Montana DNRC Fire Program

2004 Program Audit Recommendations

| Recommendation Title & Number | Specific Recommendation: | Due Date | Status: | Comments: |
| --- | --- | --- | --- | --- |
| 1. Two-Tiered Rate for Severity | DNRC with NRCG establish a two-tiered rate system for hiring severity resources. | May 2006 | Implemented: DNRC has a 75% ‘severity rate’ within the state appendix on the Best Value Contract. Additionally, a 50% reduced rate for severity has been negotiated for use of local government resources. | Success was mixed with implementation of this recommendation during the 2005-2007 wildfire seasons, as some contractors were not available if hired on severity at a reduced rate. Resources were available during the early and late season periods, but seldom during the height of the fire season. |
| 2. Fire Program Analysis (FPA) | Complete the Fire Program Analysis and report to 2007 Legislature. | January 2007 | Being Implemented: The initial FPA process has proven to be unreliable, so a different fire model (CFES) was used to analyze portions of the DNRC Fire Program. The FPA effort has been modified using features of the CFES model and DNRC remains actively involved in the development of a prototype project in Northwest Montana. | DNRC will evaluate the utility of the new FPA model and determine if the complete DNRC Fire Program should be analyzed. |
| 3. County Coop program support | DNRC seek additional funding for the County Coop portion of the program. | January 2007 | Implemented: Completed during the 2005 Legislature. Westside County Coop program restored and additional support to entire program. Four new FTE and $602k+ in new funding allocated. | Four positions hired (1 ea. @ ELO, CLO, NWLO, & EDC) and 30 new T6 engines developed for delivery to counties to date. Annual work plan includes 15 new county engines to be developed and delivered to priority counties. |
| 4. Risk Financing Fund | DNRC see legislation to establish a formal risk financing method to be used for severity funding, increasing effectiveness of IA, and reducing the risk of wildfires. | January 2007 | Implemented: Proposal submitted to 2005 Legislature but not approved. | DNRC does not intend to reintroduce this type of proposal. Procurement of severity resources will continue to be based upon wildfire risk and activity, and charged to the fire suppression account created by the 2007 special legislative session. Fuel reduction projects on private lands will continue to be financed primarily by federal funds. DNRC will continue to utilize severity resources for fuel reduction and other project accomplishments if fire conditions allow. |
| 5. Standardized payment to local fire departments | A. Develop and distribute one contract template. B. Clarify language in NWCG Business Handbook C. Provide clear direction to DNRC staff. | May 2005 | Implemented: Completed via DNRC Fire Business Committee and ongoing line officer meetings, advisory committee meetings, and NRCG/DNRC business committee meetings. | Implementation of the Incident Rental Agreement has helped to separate and standardize hiring of local government resources. Additional training and updates for DNRC and local government is ongoing. |
| 6. Equipment Inspections on project fires. | A. Including language in the Delegation of Authority specifying on-site inspections of equipment will be conducted and documented. B. Working with NRCG to address the issue of adequate resources to conduct equipment inspections on fire managed by IMTs. | May 2005 | Implemented: Delegation of Authority language was presented at DNRC Line Officer training in spring of 2005 with model language provided. Two equipment inspection workshops were held in 2005 to train NRCG agency employees for conducting equipment inspections. Additionally another interagency workshop was held in spring 2006 with three DNRC employees attending. | Equipment Manager positions on IMTs remain difficult to fill, which inhibits the ability to adequately implement this recommendation. Contractor inspections used in 2007 for preseason inspections on Best Value equipment. Expanding use of contract inspectors to IMTs and specific incidents may also improve inspections and reduce costs. |
| 7. Damage Claim Process Changed | A. Change the language in future equipment contract to reflect damage clauses used on national engine and aviation contracts. B. Provide all DNRC staff responsible for settling contract damage claims direction through revised department policy and training. | May 2005 | Implemented: A. Contract language has been changed to implement this recommendation. B. DNRC staff now has new direction related to processing fire claims in the 300 Manual. IBA training has been conducted annual since 2004 to teach employees these changes. | Incident Business Management training remains an ongoing workload with process changes and new employees. |
| 8. Delegation of Authority | A. Work with federal and other partners to improve and expand the Delegation of Authority language. B. Include more specific direction in the Fire & Aviation Management 900 Policy Manual on the development of Delegations of Authority. C. Change the Delegation of Authority format to provide more specific guidance on cost containment expectations. | May 2005 | Implemented: A. Work completed on updating the training for DNRC Line Officers regarding their use of Delegations of Authority. Line Officer training in 2004 -2007 included these changes. B. The 900 Manual has been edited to provide more specific direction for DNRC Line Officers regarding development of Delegations of Authority and use of Incident Business Advisors. C. The Delegation of Authority format has not been significantly changed, but does allow for specific cost containment expectations to be included. | Significant progress has been made in standardizing the DOA format while allowing for tailoring the document to fit circumstances related to each incident. This has helped clarify expectations for IMTs during the in briefing, and throughout management of the incident. |
| 9. Cost Share Agreements | A. Providing additional training and mentoring opportunities to Line Officers. B. Assigning a specialist to assist Land Officers with cost share negotiations on the more complex project fires. | May 2005 and ongoing | Implemented: A. DNRC has provided additional Line Officer training and utilized mentoring opportunities in 2004- 2007. B. DNRC has increased consultation between FAMB staff, Incident Business Advisors, and Area Offices during cost share agreement negotiations to ensure state interests are protected. | A cost share template was completed in 2007 in cooperation with NRCG agencies as a model of options to utilize when negotiating cost share agreements. DNRC initiated a small ‘cost share team’ in 2007 to assist line officers with completing complex cost share agreements. Additional cost share training within NRCG agencies has been proposed for the spring of 2008. |
| 10. Incident Business Advisor (IBA) Development and Use | A. Develop a program to provide training and mentoring for IBAs B. Ensure Delegation of Authority contains direction on use of IBAs C. Aggressively implement the use of IBAs on T3 or larger fires. | May 2005 and ongoing | Implemented: A. IBA training sessions have been developed and delivered to specific DNRC employees in 2004, 2005, and 2006. B. Guidance to Line Officers --- and communication during fire season --- clearly directs Line Officers to include direction of IBA use within their Delegation of Authority. C. There have been several type 3 or larger incidents since the recommendation was accepted and on each occasion DNRC assigned an IBA to assist in cost control. D. IBA task books and guidelines, as well as an IBA performance checklist have been developed and are utilized by DNRC . | Staffing all the IBA positions needed in active fire seasons remains a large challenge. Outreach to individuals outside the fire program will remain a focus to meet this need. Success to date has been getting the IBA program established on State fires and the next program focus will be targeting specific cost areas and implementing policies consistently. |
| 11. More Effective Incident Close-outs | DNRC take better advantage of opportunities presented during close out briefings by encouraging a more detailed level of discussion. | May 2005 | Implemented: More effective close-out briefings, including better briefing guidance and outlines, were a focus of the 2005 DNRC Line Officer training session. Discussions at the 2006 and 2007 also centered on the importance of open and honest closeouts to capture lessons learned from the IMT. | NRCG is considering a change to the closeout format to focus on lessons learned and reducing the number of IMT members that participate. |
| 12. Improved IMT Performance Appraisals | A. Ensure line officers conduct detailed performance appraisals of IMTs, placing special emphasis on meeting cost containment goals. B. Submit modifications of the existing IMT appraisal form to NRCG to provide more detailed feedback of IMTs. C. Submit copies of IMT appraisals to NRCG and DNRC officials as part of an overall evaluation of the role of IMTs. | May 2005 | Being Implemented: A. IMT performance appraisals were addressed during the 2005 DNRC Line Officers meeting. B. Proposed modifications to the NRCG IMT appraisal form have not yet been submitted. C. All IMT appraisals are to be submitted to both the Agency Administrators and the NRCC Coordinator for each IMT assignment. IMT development, use, and related challenges continue to be the subject of an Agency Administrator panel discussion at the annual IMT spring meeting. | Additional work is needed to modify the IMT appraisal form. |
| 13. Improved Performance Appraisals of all Fire Personnel | A. Establish formal, comprehensive, and meaningful performance measures for all personnel assigned to fire incidents. B. Adopt the recommendations of its NRCG Business Management Committee regarding performance appraisals for contracted resources. C. Incorporate requirements for performance appraisals to be conducted by IMT personnel of all contracted, as well as state/federal resources into each fire’s delegation of authority. D. Compile and analyze the performance appraisal results as part of the personnel resource ordering/selection process. | May 2005 | Implemented: A. Performance appraisal form for all wildfire personnel has been developed. B. Performance appraisals will be incorporated into Best Value Contract awards beginning spring 2007. All agency personnel are required to receive performance appraisals through NRCG and agency administrator direction. C. Incorporated into Delegation of Authority for all teams on DNRC wildfires. D. Performance appraisals utilized during IMT member selection process; application to resource ordering, sign-up, and selection in other facets is ongoing with Best Value Contracting and other agency processes. | DNRC will continue to monitor and ensure past performance is considered during selection and ordering process whenever possible. |
| 14. Payment to Contractors for Suppression on Accidental Wildfires | Clarify DNRC’s policy outlining conditions on when it will and will not pay individuals and industry for assisting in suppression efforts on accidentally started wildfires. | May 2005 | Implemented: Policy has been reviewed, and issue has been clarified and addressed during 2005 Line Officer training. Contractors will be paid for suppression efforts only when specifically ordered, and meeting qualifications for fireline duties. |  |
| 15. Improve Controls Over Cache Items | A. Include more specific language in each fire’s Delegation of Authority requiring IMT’s to establish tighter controls over fire cache items. B. Require DNRC line officers to ensure fire cache controls on fires are being followed. C. Modify department policy regarding acceptable fire cache losses so it is more I line with NRCG policy. | May 2005 | Implemented: A. Incorporated into revised Delegation of Authority, and focus of closeout meetings with IMTs during 2005 wildfire season. B. Fire cache controls and loss rates are a component of DNRC line officers performance appraisals. C. Department guidelines have been modified to better align with NRCG policy. This will be an ongoing focus of training for DNRC Line Officers. | Loss rate in 2007 was 4% for durable items. DNRC policy established an acceptable durable loss ratio of 6%. |
| 16. Competitive Bidding for Wildfire Contracting | DNRC should continue efforts to solicit competitive proposals. | May 2006 | Implemented: Competitive bidding for lunches, portable toilets, ice, hand wash stations, and rental cars has been implemented within DNRC. All NRCG members, including DNRC, have implemented Best Value Contracting for water handling equipment for 2006 wildfire season. | Additional bidding processes for 2008 for NRCG agencies include: Type 3 Caterers, Faller Modules, GIS Units, Tents/Yurts, Helicopter Support Trailers, Communication Trailers, Crash Rescue Trucks, Gray Water Trucks, and Service/Shop Trucks. Heavy Equipment is slated for a 2009 bid date. |
| 17. Use of Rented vs. Purchased Equipment | A. Actively examine cost benefits of renting versus purchasing items for wildfire suppression. B. Along with NRCG partners, reexamine fire cache contents to determine whether changes should occur as a result of 2003 fire season experiences. | May 2005 and ongoing | Being Implemented: A. No comprehensive analysis (or report) has been produced to date, but issue is pending before DNRC Fire Business Committee. B. NRCG Cache managers continue to review the equipment contained in the cache, and determine efficacy of purchasing items currently rented. | DNRC analysis will likely lead to a proposed change in DNRC policy for these types of purchases. Some fire equipment in the 2007 fire season was leased with the option to purchase. |
| 18. Cross Training for Cost Recovery and Auditing Fire Invoices | DNRC immediately begin cross-training other staff for FEMA cost recovery efforts and review of federal fire bills. | Ongoing | Implemented: New DRNC fire business specialist was hired fall 2005, and is involved with Best Value Contracting and cost recovery processes. | Cost Savings: Long-term continuation of cost recovery processes with FEMA and auditing of fire billing is essential to minimizing net costs to state of Montana from wildfires. Additional staffing has been needed to meet timelines for bill submittal to other agencies as well as providing accurate costs for the legislature and budget office. |
| 19. Retrospective Cost Studies of Wildfires | DNRC employ formal retrospective cost studies in order to examine efficiency and effectiveness of wildland fire suppression efforts and provide results to fire managers. | May 2005 and ongoing | Being Implemented: “After action” and post season fire reviews are conducted following each wildfire incident. Incorporating cost containment principles into this process is not complete, however, and will continue to be a focus for line officers and fire and aviation staff. | Cost Savings: Both types of fire reviews continue to reinforce the importance of wildfire prevention, and adequate preparedness for DNRC and local government wildfire resources as one of the most effective method of cost containment of wildfires. |
| 20. Strengthen Capabilities of Line Officers | A. Sending line officers to regional and national training when feasible. B. Encouraging the use of training assignments to gain additional practical experience. C. Requiring the line officer to order an IBA on all type 3 or larger fires. D. Assigning an experienced person to assist the line office on Type I fires and when requested for other fires. | May 2005 and ongoing | Implemented: A. DNRC line officers generally attend regional or national training corresponding to their positions on Incident Management Teams. Other training for line officers is typically within the state and most notably the annual spring line officer meeting. B. Training or off-area assignments have been used by several DNRC line officers (or trainees) within the past few years. C. Use of an IBA on all type 3 or larger fires is now an expectation understood by all line officers. However, there may be circumstances where and IBA is not used on type 3 wildfires, depending on duration. D. Line officer representatives will continue to be ordered and used for all type 1 or area command situations, and as needed to maintain adequate span of control for the primary line officer. | In 2005, DNRC line officers on incident management teams have assisted with management of hurricane recovery from both Katrina and Rita incidents. Several line officers (or those who are available to function as line officer representatives) have also been assisting the states of Oklahoma and Texas in managing their unprecedented wildfires in February/March 2006. |
| 21. Increase Involvement of Dispatch Centers in Wildfire Administration | DNRC in cooperation with other fire protection agencies, explore options to more consistently involve dispatch in discussing, evaluating, and documenting the role of dispatch in a fire’s administration. | May 2005 | Being Implemented: NRCC dispatchers routinely attend NRCG board meetings. An individual dispatch review has been completed at the Missoula Dispatch center, and a series of meetings with dispatch centers around the state discussing roles and responsibilities is ongoing. Dispatch center managers attended most DNRC post-season reviews of the 2006 season, and are expected to attend forthcoming 2007 reviews as well. Meetings are also scheduled to discuss contracting issues with all dispatch center managers in the geographic area. | More work is needed to reinforce the importance of dispatch centers in wildfire protection in Montana, and to engage third and second level dispatch center managers in wildfire planning and coordination meetings. Adequate levels of DNRC support in the interagency dispatch centers are a growing concern by interagency partners. DNRC received additional funding ($80k) for interagency dispatch support from the 2007 Legislature but increased professional level dispatch staff is also an ongoing need. |
| 22. Increase Helitack Capability | DNRC request appropriations for sufficient personal services to provide for a continuous helitack capability for each helicopter assigned to land offices during the fire season. | January 2007 | Implemented: All helitack crews (one foreman and three crew members) were operational at DNRC initial attack stations in Kalispell, Missoula, and Helena during the summer of 2005, 2006, and 2007. | Additional helitack capacity not only improved the effectiveness of air operations last season, but also improved the coordination and safety focus due to creation of full-time aviation managers at NWLO, SWLO, and CLO. However, additional staffing is still needed to provide manager, crew, and fuel support for two of the DNRC helicopters. |
| 23. Increase Aviation Pilot Personnel | DNRC request sufficient personal services resources to safely and effectively operate all assigned aircraft and more accurately reflect actual pilot operating requirements. | January 2005 | Implemented: Three additional seasonal pilots have been hired, making a total of two full-time and five seasonal pilots for the helicopter portion of the aviation program. | Additional pilots allowed DNRC to field 7-day coverage with all aircraft during most of the 2005 and 2006 fire seasons, with assistance from short-term hiring of two “on-call” pilots. During the 2007 wildfire season, the “on-call” pilots were not available to fly DNRC aircraft, resulting in some days with less than 100% coverage from all DNRC aircraft. DNRC helicopters were instrumental in success of suppression efforts on numerous fires around the state since the hiring of the three additional pilots, but two more would be required to ensure 7-day coverage with all aircraft for the entire core fire season. Cost Savings: Conservative estimate is likely over $15-20 million due to better coverage of DNRC aircraft. |
| 24. Increase Aviation Mechanic Personnel | DNRC request sufficient personal services to properly staff its aviation maintenance program. | January 2005 | Implemented: Three full-time aviation mechanics have been hired, increasing the total to five full-time mechanics for maintaining 7 helicopters and 3 fixed-wing aircraft. | Additional mechanic support has enabled construction and use of a new tail-boom jig for improving performance of UH-1 helicopters, construction of paint booth for savings of $20,000 per aircraft, continued development of fifth UH-1 helicopter (88M), and overall ability to have rested and adequate mechanical support for the aviation assets. |
| 25. Legislative Study of Wildfire Statutes and Wildfire Policy | Legislature authorize a study to develop and update fire-related statutes to address current development and environmental conditions and improve wildland fire suppression management and mitigation. | January 2007 | Implemented: HJR10 (Jacobsen) was referred to the EQC, and a workgroup convened by the EQC has met since summer 2005 to revise statutes, develop state wildfire policy, clarify roles and responsibilities, and consider development standards for the wildland-urban interface. Proposed legislation was introduced to the 2007 Legislature with several bills becoming law. | HB 112, SB 103, SB 130, SB 145, SB 147, SB 51, & SB 404 all became law. Rule making for several of the laws will be undertaken winter of 2008 by DNRC. |
| 26. Clarify Wildfire Responsibilities with Local Government | DNRC establish formal agreements with local fire service organizations to clarify responsibilities and compensation for responding to DNRC fires occurring outside the statutorily designated fire season. | June 2005 and ongoing | Implemented: DNRC has initiated two processes to address this recommendation: Incorporate mutual aid concept into operating agreements that authorize use of DNRC equipment without a formal county assistance request during the initial attack period. Payment to local government within their jurisdiction would commence at the end of the IA period, if requested by DNRC. Payment agreements are being negotiated with local government fire departments to authorize payment for initial attack on DNRC protection when DNRC resources are unable or inadequate to respond. | Efforts to ensure consistency with such agreements have been difficult to achieve, but both efforts will have a tremendous effect on relationships with local government, improve initial attack effectiveness, and reinforce capacity of local government fire departments. |
| 27. Create Type 3 Incident Management Teams | DNRC present to the NRCG and Legislature a proposal for the formation, maintenance, and funding of additional Type 3 Incident Management Teams for Montana. | January 2007 and ongoing | Implemented: DNRC introduced this decision package during the 2005 legislature joint budget subcommittee, but it was not approved by the full House Appropriations Committee. | DNRC is not planning to reintroduce a legislative proposal for this recommendation. There are concerns over the ability of wildland fire resources, and the training organization, to support additional type 3 teams sponsored by DNRC, given the difficulties in maintaining the Type 1 and 2 IMT rosters. The Type 3 County Assistance Team continues to be sponsored by DNRC, but is limited in scope and duration due to its roster of volunteer members. Type 3 interagency IMT pools are under development within the Bozeman, Billings, and western Montana areas, but are struggling to maintain an adequate pool of qualified personnel to draw from. |